MEAL & Project Cycle Management (PCM)

Consolidated Master Technical Guide & Answer Key

Section 1: Project Cycle Management & Logical Framework

1. Phases of the Project Cycle

Programming (Programmation): Defines general orientation, priorities, and principles based on problem analysis and local capacities. Results in a Country Strategy Paper.

Identification (Identification): Analyzes stakeholder needs and interests; identifies and examines project ideas through sector/pre-feasibility studies.

Formulation / Appraisal (Instruction / Conception): Detailed examination of the project idea, detailed work plans, Logical Frameworks (with indicators, targets, and timelines), and budget allocation. Results in a funding proposal.

Financing (Financement): Project proposal review by internal/external financing committees, leading to a formal grant/financing agreement signature.

Implementation (Mise en œuvre): Execution of planned activities using allocated resources to achieve outputs and specific objectives while maintaining continuous monitoring.

Evaluation (Évaluation): Systematic and objective assessment of an ongoing or completed project regarding its relevance, efficiency, effectiveness, impact, and sustainability.

2. Logical Framework (Cadre Logique)

Definition & Purpose: A matrix summarizing the operational design of a project, detailing the cause-and-effect relationship between activities, outputs, outcomes, and impact, along with Objectively Verifiable Indicators (OVIs), Means of Verification (MoVs), and assumptions.

| Component | Definition / Scope |
| --- | --- |
| Goal / Overall Objective (Objectif Global) | The broader long-term developmental impact to which the project contributes. |
| Specific Objectives / Outcomes (Objectifs Spécifiques) | Direct benefits and institutional/behavioral changes achieved by project end. |
| Outputs / Expected Results (Résultats Attendus) | Concrete deliverables and immediate products resulting from project activities. |
| Activities (Activités) | Specific tasks and processes executed to produce outputs. |
| Objectively Verifiable Indicators (OVIs / IOV) | Quantitative and qualitative measures used to verify progress at each level. |
| Means of Verification (Moyens de Vérification) | Specific data sources and methods used to obtain indicator measurements. |
| Assumptions (Hypothèses) | External factors outside direct project control required for success. |

3. Risk vs. Assumption

Assumption (Hypothèse): A positive statement regarding external conditions outside the project manager's direct control needed for success. Example: "The judicial procedural reform is successfully enacted by parliament."

Risk (Risque): An uncertain event or negative condition that could prevent project success. Example: "Judicial procedural reform fails due to political instability."

Section 2: Monitoring, Evaluation, Accountability, and Learning (MEAL)

1. Monitoring vs. Evaluation

| Criteria | Monitoring (Suivi) | Evaluation (Évaluation) |
| --- | --- | --- |
| Purpose | Track operational progress, resource use, and process efficiency; trigger real-time adjustments. | Assess causality, achievement of objectives, overall relevance, impact, and sustainability. |
| Focus | Inputs, Activities, and Outputs (Process & short-term tracking). | Outcomes, Impact, and Strategic Causal Chains. |
| Timing / Frequency | Continuous / Periodic (Daily, Monthly, Quarterly). | Episodic (Ex-ante, Mid-term, Endline, Ex-post). |
| Primary Data | Internal progress reports, attendance lists, routine registries. | Baseline/Endline surveys, external evaluations, case studies. |

2. Typology of Evaluations (Time-based)

Ex-Ante Evaluation: Done prior to implementation during design to test feasibility and target relevance.

Mid-Term Evaluation (Évaluation à mi-parcours): Conducted mid-way to assess progress and realign strategies if necessary.

Endline / Final Evaluation: Conducted immediately upon completion to assess short-term outcome achievements.

Ex-Post Evaluation: Conducted long after project closure to assess long-term sustainability and impact.

In-Itinere Evaluation: Continuous evaluation throughout policy/program implementation.

3. Core Evaluation Criteria (OECD/DAC Standards)

Relevance (Pertinence): Alignment between project objectives, target population needs, and context realities.

Effectiveness (Efficacité): The degree to which objectives and expected outcomes were achieved.

Efficiency (Efficience): Optimal conversion of inputs (funding, time, HR) into outputs at minimal cost.

Sustainability (Pérennité / Durabilité): Continuation of benefits after donor funding ends.

Utility (Utilité): Overall societal value of unintended positive/negative effects compared to initial needs.

4. Quality Benchmark & Key MEAL Tools

Quality Benchmark (QB): Essential MEAL standards used to track and verify quality against predefined technical criteria at the output/activity level.

Detailed Implementation Plan (DIP): Operational tool breaking down project activities monthly.

Project MEAL Tracker Report (PMTR / IPTT): Indicator Tracking Table tracking actual vs. targeted progress monthly/quarterly.

Do No Harm / Risk Assessment Matrix: Contextual risk tracker updated at least quarterly to ensure interventions do not trigger unintended conflict or harm.

Section 3: Data Collection, Indicators, & Quality Control

1. Indicators & Typology

Definition: A quantitative or qualitative variable providing a reliable basis to measure change over time.

SMART Criteria: Specific, Measurable, Attainable/Achievable, Realistic/Relevant, Time-bound/Trackable.

Key Dimensions: Quantity (How much?), Quality (How well?), Target Group (Who?), Timeframe (When?), Location (Where?).

Process Indicator (Indicateur de processus): Tracks activity implementation speed and input utilization (e.g., fuel consumption rate per km).

Output / Realization Indicator (Indicateur de réalisation): Direct physical outputs produced (e.g., number of people trained, number of kits distributed).

Outcome / Result Indicator (Indicateur d'effet): Intermediate behavioral or institutional changes (e.g., % of women washing hands with soap).

Impact Indicator (Indicateur d'impact): Long-term goal achievement (e.g., reduction in child malnutrition rate).

2. Quantitative vs. Qualitative Data

| Attribute | Quantitative Data | Qualitative Data |
| --- | --- | --- |
| Nature | Numerical values, counts, ratios, percentages. | Textual descriptions, perceptions, beliefs, narratives. |
| Focus | How many? How much? What proportion? | Why? How? What are the underlying reasons? |
| Analysis | Statistical analysis, pivot tables, cross-tabulations. | Thematic coding, narrative summaries, content analysis. |
| Examples | 1. 40% of households walk >2h for water. 2. 64 communities connected to early warning systems. 3. 150 health workers trained. | 1. Focus group discussions revealing fear of night travel to water points. 2. Community perceptions on warning system siren clarity. 3. Stories of change from women committee members. |

3. Data Quality Assessment (DQA) Criteria

Validity (Validité): Data clearly represents the intended result and is free from bias.

Reliability / Consistency (Fiabilité / Constance): Collection methods produce consistent results over repeated measurements.

Precision (Précision): Sufficient detail and minimal margin of error.

Integrity (Intégrité): Data is secure from manipulation, fraud, or unauthorized modification.

Timeliness (Périodicité / Actualité): Data is updated and available when needed for decision-making.

4. Data Collection Technologies (ODK, KoboCollect)

Key Advantages:

Reduced printing/paper costs and immediate digital encoding.

Elimination of manual data entry errors.

Multi-media collection capabilities (GPS points, photos, audio recordings).

Real-time field oversight and data quality verification.

Key Limitations / Vulnerabilities:

Dependence on battery power, charging infrastructure, and network access.

Device theft risks and physical vulnerability in harsh weather/field conditions.

Respondent intimidation or mistrust regarding digital devices.

Server outages halting data flow.

Section 4: Accountability, Feedback Mechanisms, & Do No Harm

1. Humanitarian Accountability Partnership (HAP) Standards

HAP principles require organizations to uphold accountability to crisis-affected populations through:

Information Sharing: Openly sharing mission, budget, target selection criteria, and rights.

Participation: Involving beneficiaries (including vulnerable groups) in decision-making across all project stages.

Complaints & Feedback Mechanisms (CRM): Establishing safe, accessible, and confidential channels for complaints.

Competence & Staff Learning: Training staff on behavioral standards and code of conduct.

2. Comparative Matrix of Feedback & Complaints Mechanisms

| Mechanism | Advantages | Disadvantages | Best Practice / Context |
| --- | --- | --- | --- |
| Suggestion Box (Boîte à suggestions) | Anonymous; low operational cost; available 24/7. | Inaccessible to illiterate individuals; requires routine physical retrieval. | Good for long-term projects; use visual symbols/logos on boxes. |
| Toll-Free Hotline (Ligne verte) | Direct contact; accessible to illiterate beneficiaries; instant response. | Network coverage issues; requires dedicated phone operators; excludes those without phones. | Best in urban/semi-urban settings; employ both male & female operators. |
| Face-to-Face (Face à Face) | Highly accessible; allows clarification of complex details; builds trust. | Lack of privacy for sensitive complaints; time-intensive for field staff. | Essential for short-term emergency projects and remote illiterate communities. |
| Complaints Management Committee (Comité de gestion) | High community ownership; locally accessible; cost-effective. | Risk of elite capture or bias; non-anonymous; requires oversight against power abuse. | Train diverse representation (women, youth, minority groups); maintain logbooks. |

3. "Do No Harm" Principle (Ne Pas Nuire)

An operational principle ensuring humanitarian and development interventions do not inadvertently exacerbate existing social conflicts, create security risks, or compromise the dignity/safety of vulnerable populations.

Example Conflict Scenario: Distributing assistance in a central village causes neighboring armed groups to target the beneficiaries.

Mitigation Strategy: Transition to decentralized, discreet distributions or voucher systems after consulting local community protection committees.

Section 5: Sampling Methods & Formulas

1. Sampling Techniques Matrix

| Method | Definition | Advantages | Disadvantages |
| --- | --- | --- | --- |
| Simple Random Sampling (Aléatoire simple) | Every population element has an equal probability of selection. | Unbiased; straightforward analysis. | Requires a complete and updated sampling frame list. |
| Systematic Sampling (Systématique) | Selection based on a fixed interval k = N/n starting from a random point. | Easy to execute in field surveys without full prior lists. | Risk of periodicity bias if data has recurring patterns. |
| Stratified Sampling (Stratifié) | Population divided into distinct subgroups (strata); independent sampling within each. | High representation across heterogenous groups/zones. | Higher administrative cost; requires prior knowledge of strata parameters. |
| Cluster Sampling (En grappes) | Population divided into naturally occurring groups (e.g., villages); entire clusters selected randomly. | Reduces travel time and field logistics costs. | Higher design effect; units within clusters may be overly homogeneous. |

2. Sample Size Calculation Formula

The standard formula for estimating sample size for proportions in large populations (N > 20,000) is:

n = (z² · p · (1 - p)) / d²

n = Sample size required

z = Confidence level score (e.g., 1.96 for 95% confidence level, 2.575 for 99%)

p = Estimated proportion of population attribute (default p = 0.5 if unknown)

d = Margin of error / Precision (e.g., 0.05 for ±5%)

Section 6: Key Formulas & Analytical Exercises

1. Specific Outcome Calculation Formula

Indicator: Percentage of sexual assault survivors receiving medical care within 72 hours.

Percentage (%) = [ (Survivors receiving care within 72 hrs) / (Total survivors reported) ] × 100

2. Analytical Interpretation: WASH Survey Table (Baseline vs. Endline)

Data Summary:

Daily Activities (Activités quotidiennes): Protected source dropped from 11% to 8%; Unprotected source dropped from 39% to 16%; Handpump increased significantly from 9% to 48%.

Drinking Water (Consommation): Handpump usage increased from 21% to 66%; River/Rainwater usage dropped from 12% to 1%.

Rainy Season Usage (Saison des pluies): Unprotected source usage dropped from 43% to 20%; Handpump usage dominated endline at 60%.

Analytical Takeaways:

Behavioral Shift Towards Improved Sources: The intervention achieved substantial positive health impact by shifting community reliance away from open rivers and unprotected wells toward borehole handpumps for drinking (increasing to 66%).

Seasonal Stabilization: Improved infrastructure reduced seasonal vulnerability during rains, preventing spikes in waterborne diseases.

Targeted Maintenance Need: Protected springs showed minor decline/underutilization relative to pumps, indicating a need for local water committee capacity building for spring maintenance.